## June 2026
Resource Name | POD Name | Work Package Code | Rate | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Total Hours | Fee | Group PM
Edmund Blackadder | Cobra POD | GBL0007741.2.11 | 185 | 16 | 24 | 28 | 28 | 5
S. Baldrick | Cobra POD | GBL0007741.2.11 | 95 | 37 | 39 | 38 | 36 | 16
George St. Barleigh | Cobra POD | GBL0007741.2.11 | 130 | 37 |  | 37 | 34 | 13
Nurse Darling | Viper POD | GBL0007741.2.22 | 140 | 36 | 31 | 36 | 34 | 12
Gen. Melchett | Viper POD | GBL0007741.2.22 | 210 | 21 | 25 | 17 | 20 | 5
Capt. Kevin Darling | Viper POD | GBL0007741.2.22 | 120 | 29 | 30 | 38 | 32 | 10
Bobbie Parkhurst | Python POD | GBL0007741.2.33 | 125 | 40 | 41 | 36 | 38 | 14
Doris Miggins | Python POD | GBL0007741.2.33 | 135 | 41 | 37 | 36 | 38 | 16
Lord Percy Percy | Python POD | GBL0007741.2.33 | 145 | 33 | 32 | 32 | 31 | 10
Mrs. Miggins | Cobra POD | GBL0007741.2.11 | 115 | 28 | 28 | 25 | 29 | 14
TOTAL

## Details June 2026
Client | Name | Date | Project | WBS | Project role | Feature | PBI | Description | Logged time (hours) | Rate | Rate per MD/per hour | Total fee | Week num
Deloitte UK | Edmund Blackadder | 2026-06-01 | Cobra POD | GBL0007741.2.11 | Senior Manager | Reporting | PBI-1029 | Budget review - numbers adjusted for palatability | 6 | 185 | per hour | 1110
Deloitte UK | Edmund Blackadder | 2026-06-03 | Cobra POD | GBL0007741.2.11 | Senior Manager | Analytics | PBI-1004 | Scope negotiation - cunning redefinition of "done" | 6 | 185 | per hour | 1110
Deloitte UK | Edmund Blackadder | 2026-06-04 | Cobra POD | GBL0007741.2.11 | Senior Manager | Performance | PBI-1029 | Scope negotiation - cunning redefinition of "done" | 4 | 185 | per hour | 740
Deloitte UK | Edmund Blackadder | 2026-06-08 | Cobra POD | GBL0007741.2.11 | Senior Manager | Notifications | PBI-1006 | Executive reporting - made bad news sound acceptable | 6 | 185 | per hour | 1110
Deloitte UK | Edmund Blackadder | 2026-06-09 | Cobra POD | GBL0007741.2.11 | Senior Manager | Analytics | PBI-1036 | Governance compliance - ticked all the boxes | 7 | 185 | per hour | 1295
Deloitte UK | Edmund Blackadder | 2026-06-10 | Cobra POD | GBL0007741.2.11 | Senior Manager | Analytics | PBI-1042 | Governance compliance - ticked all the boxes | 4 | 185 | per hour | 740
Deloitte UK | Edmund Blackadder | 2026-06-11 | Cobra POD | GBL0007741.2.11 | Senior Manager | Authentication | PBI-1029 | Risk management - identified risk of client noticing delays | 7 | 185 | per hour | 1295
Deloitte UK | Edmund Blackadder | 2026-06-15 | Cobra POD | GBL0007741.2.11 | Senior Manager | User Management | PBI-1042 | Executive reporting - made bad news sound acceptable | 6 | 185 | per hour | 1110
Deloitte UK | Edmund Blackadder | 2026-06-16 | Cobra POD | GBL0007741.2.11 | Senior Manager | Performance | PBI-1034 | Governance compliance - ticked all the boxes | 5 | 185 | per hour | 925
Deloitte UK | Edmund Blackadder | 2026-06-17 | Cobra POD | GBL0007741.2.11 | Senior Manager | Infrastructure | PBI-1019 | Budget review - numbers adjusted for palatability | 5 | 185 | per hour | 925
Deloitte UK | Edmund Blackadder | 2026-06-18 | Cobra POD | GBL0007741.2.11 | Senior Manager | Notifications | PBI-1042 | Stakeholder management - kept them from bothering real team | 6 | 185 | per hour | 1110
Deloitte UK | Edmund Blackadder | 2026-06-19 | Cobra POD | GBL0007741.2.11 | Senior Manager | User Management | PBI-1044 | Executive reporting - made bad news sound acceptable | 6 | 185 | per hour | 1110
Deloitte UK | Edmund Blackadder | 2026-06-22 | Cobra POD | GBL0007741.2.11 | Senior Manager | Infrastructure | PBI-1006 | Risk management - identified risk of client noticing delays | 6 | 185 | per hour | 1110
Deloitte UK | Edmund Blackadder | 2026-06-23 | Cobra POD | GBL0007741.2.11 | Senior Manager | Data Migration | PBI-1042 | Budget review - numbers adjusted for palatability | 5 | 185 | per hour | 925
Deloitte UK | Edmund Blackadder | 2026-06-24 | Cobra POD | GBL0007741.2.11 | Senior Manager | Analytics | PBI-1046 | Risk management - identified risk of client noticing delays | 7 | 185 | per hour | 1295
Deloitte UK | Edmund Blackadder | 2026-06-25 | Cobra POD | GBL0007741.2.11 | Senior Manager | Notifications | PBI-1022 | Team motivation - threatened mild inconveniences | 6 | 185 | per hour | 1110
Deloitte UK | Edmund Blackadder | 2026-06-26 | Cobra POD | GBL0007741.2.11 | Senior Manager | User Management | PBI-1024 | Team motivation - threatened mild inconveniences | 4 | 185 | per hour | 740
Deloitte UK | Edmund Blackadder | 2026-06-30 | Cobra POD | GBL0007741.2.11 | Senior Manager | Performance | PBI-1013 | Budget review - numbers adjusted for palatability | 5 | 185 | per hour | 925
Deloitte UK | S. Baldrick | 2026-06-01 | Cobra POD | GBL0007741.2.11 | Junior Developer | Reporting | PBI-1005 | Cunning plan - the one involving a turnip | 7 | 95 | per hour | 665
Deloitte UK | S. Baldrick | 2026-06-02 | Cobra POD | GBL0007741.2.11 | Junior Developer | User Management |  | Cunning plan implementation - stage 2 (revised) | 8 | 95 | per hour | 760
Deloitte UK | S. Baldrick | 2026-06-03 | Cobra POD | GBL0007741.2.11 | Junior Developer | Analytics | PBI-1009 | Support ticket resolution - something went wrong | 6 | 95 | per hour | 570
Deloitte UK | S. Baldrick | 2026-06-04 | Cobra POD | GBL0007741.2.11 | Junior Developer | Reporting | PBI-1012 | Cunning plan - the one involving a turnip | 9 | 95 | per hour | 855
Deloitte UK | S. Baldrick | 2026-06-05 | Cobra POD | GBL0007741.2.11 | Junior Developer | Authentication | PBI-1027 | Unit tests - mostly passing | 7 | 95 | per hour | 665
Deloitte UK | S. Baldrick | 2026-06-08 | Cobra POD | GBL0007741.2.11 | Junior Developer | Performance | PBI-1040 | Cunning plan debugging - turnip not working | 8 | 95 | per hour | 760
Deloitte UK | S. Baldrick | 2026-06-09 | Cobra POD | GBL0007741.2.11 | Junior Developer | API Integration | PBI-1035 | Unit tests - mostly passing | 8 | 95 | per hour | 760
Deloitte UK | S. Baldrick | 2026-06-10 | Cobra POD | GBL0007741.2.11 | Junior Developer | Performance | PBI-1013 | Cunning plan v3 - considerably less cunning | 7 | 95 | per hour | 665
Deloitte UK | S. Baldrick | 2026-06-11 | Cobra POD | GBL0007741.2.11 | Junior Developer | Performance | PBI-1030 | Documentation - added some words | 8 | 95 | per hour | 760
Deloitte UK | S. Baldrick | 2026-06-12 | Cobra POD | GBL0007741.2.11 | Junior Developer | User Management | PBI-1034 | Code review feedback implementation | 8 | 95 | per hour | 760
Deloitte UK | S. Baldrick | 2026-06-15 | Cobra POD | GBL0007741.2.11 | Junior Developer | API Integration | PBI-1039 | Cunning plan - the one involving a turnip | 9 | 95 | per hour | 855
Deloitte UK | S. Baldrick | 2026-06-16 | Cobra POD | GBL0007741.2.11 | Junior Developer | Authentication | PBI-1042 | Cunning plan v3 - considerably less cunning | 7 | 95 | per hour | 665
Deloitte UK | S. Baldrick | 2026-06-17 | Cobra POD | GBL0007741.2.11 | Junior Developer | User Management | PBI-1007 | Support ticket resolution - something went wrong | 9 | 95 | per hour | 855
Deloitte UK | S. Baldrick | 2026-06-18 | Cobra POD | GBL0007741.2.11 | Junior Developer | Dashboard | PBI-1049 | Cunning plan v3 - considerably less cunning | 6 | 95 | per hour | 570
Deloitte UK | S. Baldrick | 2026-06-19 | Cobra POD | GBL0007741.2.11 | Junior Developer | Performance | PBI-1033 | Cunning plan v3 - considerably less cunning | 7 | 95 | per hour | 665
Deloitte UK | S. Baldrick | 2026-06-22 | Cobra POD | GBL0007741.2.11 | Junior Developer | Dashboard | PBI-1015 | Code review feedback implementation | 7 | 95 | per hour | 665
Deloitte UK | S. Baldrick | 2026-06-23 | Cobra POD | GBL0007741.2.11 | Junior Developer | Authentication | PBI-1027 | Support ticket resolution - something went wrong | 9 | 95 | per hour | 855
Deloitte UK | S. Baldrick | 2026-06-24 | Cobra POD | GBL0007741.2.11 | Junior Developer | User Management | PBI-1024 | Code review feedback implementation | 6 | 95 | per hour | 570
Deloitte UK | S. Baldrick | 2026-06-25 | Cobra POD | GBL0007741.2.11 | Junior Developer | Dashboard | PBI-1024 | Code review feedback implementation | 7 | 95 | per hour | 665
Deloitte UK | S. Baldrick | 2026-06-26 | Cobra POD | GBL0007741.2.11 | Junior Developer | Infrastructure | PBI-1007 | Cunning plan implementation - stage 1 | 7 | 95 | per hour | 665
Deloitte UK | S. Baldrick | 2026-06-29 | Cobra POD | GBL0007741.2.11 | Junior Developer | Reporting | PBI-1003 | Cunning plan - the one involving a turnip | 8 | 95 | per hour | 760
Deloitte UK | S. Baldrick | 2026-06-30 | Cobra POD | GBL0007741.2.11 | Junior Developer |  |  | Unit tests - mostly passing | 8 | 95 | per hour | 760
Deloitte UK | George St. Barleigh | 2026-06-01 | Cobra POD | GBL0007741.2.11 | Senior Developer | Performance | PBI-1029 | Project governance documentation | 7 | 130 | per hour | 910
Deloitte UK | George St. Barleigh | 2026-06-02 | Cobra POD | GBL0007741.2.11 | Senior Developer | Authentication | PBI-1017 | Sprint planning and backlog grooming | 6 | 130 | per hour | 780
Deloitte UK | George St. Barleigh | 2026-06-03 | Cobra POD | GBL0007741.2.11 | Senior Developer | User Management | PBI-1047 | User story refinement with client team | 7 | 130 | per hour | 910
Deloitte UK | George St. Barleigh | 2026-06-04 | Cobra POD | GBL0007741.2.11 | Senior Developer | Data Migration | PBI-1016 | Sprint planning and backlog grooming | 9 | 130 | per hour | 1170
Deloitte UK | George St. Barleigh | 2026-06-05 | Cobra POD | GBL0007741.2.11 | Senior Developer | Authentication | PBI-1016 | Sprint planning and backlog grooming | 8 | 130 | per hour | 1040
Deloitte UK | George St. Barleigh | 2026-06-15 | Cobra POD | GBL0007741.2.11 | Senior Developer | Analytics | PBI-1030 | Vendor evaluation and procurement support | 9 | 130 | per hour | 1170
Deloitte UK | George St. Barleigh | 2026-06-16 | Cobra POD | GBL0007741.2.11 | Senior Developer | Performance | PBI-1039 | Sprint planning and backlog grooming | 6 | 130 | per hour | 780
Deloitte UK | George St. Barleigh | 2026-06-17 | Cobra POD | GBL0007741.2.11 | Senior Developer | User Management | PBI-1037 | Vendor evaluation and procurement support | 6 | 130 | per hour | 780
Deloitte UK | George St. Barleigh | 2026-06-18 | Cobra POD | GBL0007741.2.11 | Senior Developer | Reporting | PBI-1019 | Project governance documentation | 7 | 130 | per hour | 910
Deloitte UK | George St. Barleigh | 2026-06-19 | Cobra POD | GBL0007741.2.11 | Senior Developer | Analytics | PBI-1023 | Requirements gathering - stakeholder interviews | 9 | 130 | per hour | 1170
Deloitte UK | George St. Barleigh | 2026-06-22 | Cobra POD | GBL0007741.2.11 | Senior Developer | Security | PBI-1012 | Change request assessment and documentation | 7 | 130 | per hour | 910
Deloitte UK | George St. Barleigh | 2026-06-23 | Cobra POD | GBL0007741.2.11 | Senior Developer | Infrastructure | PBI-1005 | Cunning plan - revised after client feedback | 6 | 130 | per hour | 780
Deloitte UK | George St. Barleigh | 2026-06-24 | Cobra POD | GBL0007741.2.11 | Senior Developer | Performance | PBI-1003 | Client status report and dashboard update | 6 | 130 | per hour | 780
Deloitte UK | George St. Barleigh | 2026-06-25 | Cobra POD | GBL0007741.2.11 | Senior Developer | Data Migration | PBI-1048 | Risk register update and mitigation planning | 9 | 130 | per hour | 1170
Deloitte UK | George St. Barleigh | 2026-06-26 | Cobra POD | GBL0007741.2.11 | Senior Developer | Dashboard | PBI-1023 | Risk register update and mitigation planning | 6 | 130 | per hour | 780
Deloitte UK | George St. Barleigh | 2026-06-29 | Cobra POD | GBL0007741.2.11 | Senior Developer | Notifications | PBI-1041 | Project governance documentation | 7 | 130 | per hour | 910
Deloitte UK | George St. Barleigh | 2026-06-30 | Cobra POD | GBL0007741.2.11 | Senior Developer |  |  | Change request assessment and documentation | 6 | 130 | per hour | 780
Deloitte UK | Nurse Darling | 2026-06-01 | Viper POD | GBL0007741.2.22 | UX/UI Lead | Authentication | PBI-1023 | Cloud infrastructure design - AWS | 7 | 140 | per hour | 980
Deloitte UK | Nurse Darling | 2026-06-02 | Viper POD | GBL0007741.2.22 | UX/UI Lead | Reporting |  | Design system documentation | 7 | 140 | per hour | 980
Deloitte UK | Nurse Darling | 2026-06-03 | Viper POD | GBL0007741.2.22 | UX/UI Lead | Performance | PBI-1041 | Performance testing and optimisation | 8 | 140 | per hour | 1120
Deloitte UK | Nurse Darling | 2026-06-04 | Viper POD | GBL0007741.2.22 | UX/UI Lead | Dashboard | PBI-1046 | Cloud infrastructure design - AWS | 6 | 140 | per hour | 840
Deloitte UK | Nurse Darling | 2026-06-05 | Viper POD | GBL0007741.2.22 | UX/UI Lead | Data Migration | PBI-1013 | UI component library development | 8 | 140 | per hour | 1120
Deloitte UK | Nurse Darling | 2026-06-08 | Viper POD | GBL0007741.2.22 | UX/UI Lead | Authentication | PBI-1021 | CI/CD pipeline configuration | 5 | 140 | per hour | 700
Deloitte UK | Nurse Darling | 2026-06-09 | Viper POD | GBL0007741.2.22 | UX/UI Lead | Security | PBI-1035 | A/B testing framework setup | 7 | 140 | per hour | 980
Deloitte UK | Nurse Darling | 2026-06-10 | Viper POD | GBL0007741.2.22 | UX/UI Lead | Authentication | PBI-1049 | Security review and penetration testing prep | 8 | 140 | per hour | 1120
Deloitte UK | Nurse Darling | 2026-06-11 | Viper POD | GBL0007741.2.22 | UX/UI Lead | Infrastructure |  | Security review and penetration testing prep | 6 | 140 | per hour | 840
Deloitte UK | Nurse Darling | 2026-06-12 | Viper POD | GBL0007741.2.22 | UX/UI Lead | Infrastructure | PBI-1018 | Design system documentation | 5 | 140 | per hour | 700
Deloitte UK | Nurse Darling | 2026-06-15 | Viper POD | GBL0007741.2.22 | UX/UI Lead | Security | PBI-1026 | UAT test case preparation | 5 | 140 | per hour | 700
Deloitte UK | Nurse Darling | 2026-06-16 | Viper POD | GBL0007741.2.22 | UX/UI Lead | Infrastructure | PBI-1012 | Regression testing suite - automated | 8 | 140 | per hour | 1120
Deloitte UK | Nurse Darling | 2026-06-17 | Viper POD | GBL0007741.2.22 | UX/UI Lead | Performance | PBI-1024 | Performance testing and optimisation | 8 | 140 | per hour | 1120
Deloitte UK | Nurse Darling | 2026-06-18 | Viper POD | GBL0007741.2.22 | UX/UI Lead |  |  | Figma wireframes review and iteration | 7 | 140 | per hour | 980
Deloitte UK | Nurse Darling | 2026-06-19 | Viper POD | GBL0007741.2.22 | UX/UI Lead | Security | PBI-1039 | Figma wireframes review and iteration | 8 | 140 | per hour | 1120
Deloitte UK | Nurse Darling | 2026-06-22 | Viper POD | GBL0007741.2.22 | UX/UI Lead | Data Migration | PBI-1021 | A/B testing framework setup | 6 | 140 | per hour | 840
Deloitte UK | Nurse Darling | 2026-06-23 | Viper POD | GBL0007741.2.22 | UX/UI Lead | Infrastructure | PBI-1043 | Figma wireframes review and iteration | 5 | 140 | per hour | 700
Deloitte UK | Nurse Darling | 2026-06-24 | Viper POD | GBL0007741.2.22 | UX/UI Lead | Performance | PBI-1039 | Security review and penetration testing prep | 7 | 140 | per hour | 980
Deloitte UK | Nurse Darling | 2026-06-25 | Viper POD | GBL0007741.2.22 | UX/UI Lead |  |  | Cloud infrastructure design - AWS | 8 | 140 | per hour | 1120
Deloitte UK | Nurse Darling | 2026-06-26 | Viper POD | GBL0007741.2.22 | UX/UI Lead | Performance | PBI-1003 | UAT test case preparation | 8 | 140 | per hour | 1120
Deloitte UK | Nurse Darling | 2026-06-29 | Viper POD | GBL0007741.2.22 | UX/UI Lead | Security | PBI-1018 | Accessibility audit - WCAG 2.1 compliance | 7 | 140 | per hour | 980
Deloitte UK | Nurse Darling | 2026-06-30 | Viper POD | GBL0007741.2.22 | UX/UI Lead | Notifications | PBI-1041 | Figma wireframes review and iteration | 5 | 140 | per hour | 700
Deloitte UK | Gen. Melchett | 2026-06-01 | Viper POD | GBL0007741.2.22 | Cloud Architect | Reporting | PBI-1039 | Cloud architecture - MAGNIFICENT design review | 4 | 210 | per hour | 840
Deloitte UK | Gen. Melchett | 2026-06-02 | Viper POD | GBL0007741.2.22 | Cloud Architect | Reporting | PBI-1005 | Cloud architecture - MAGNIFICENT design review | 6 | 210 | per hour | 1260
Deloitte UK | Gen. Melchett | 2026-06-03 | Viper POD | GBL0007741.2.22 | Cloud Architect | Security | PBI-1037 | Architecture decision record - brilliant insight | 5 | 210 | per hour | 1050
Deloitte UK | Gen. Melchett | 2026-06-05 | Viper POD | GBL0007741.2.22 | Cloud Architect | Infrastructure | PBI-1029 | Architecture decision record - brilliant insight | 6 | 210 | per hour | 1260
Deloitte UK | Gen. Melchett | 2026-06-08 | Viper POD | GBL0007741.2.22 | Cloud Architect | Infrastructure | PBI-1026 | Executive briefing - delivered with great authority | 4 | 210 | per hour | 840
Deloitte UK | Gen. Melchett | 2026-06-09 | Viper POD | GBL0007741.2.22 | Cloud Architect | Dashboard | PBI-1002 | Technical strategy - bold and daring approach | 5 | 210 | per hour | 1050
Deloitte UK | Gen. Melchett | 2026-06-10 | Viper POD | GBL0007741.2.22 | Cloud Architect | Security | PBI-1036 | Executive briefing - delivered with great authority | 6 | 210 | per hour | 1260
Deloitte UK | Gen. Melchett | 2026-06-11 | Viper POD | GBL0007741.2.22 | Cloud Architect | Performance | PBI-1014 | AWS Well-Architected review - passed with flying colours | 5 | 210 | per hour | 1050
Deloitte UK | Gen. Melchett | 2026-06-12 | Viper POD | GBL0007741.2.22 | Cloud Architect | Performance | PBI-1013 | AWS Well-Architected review - passed with flying colours | 5 | 210 | per hour | 1050
Deloitte UK | Gen. Melchett | 2026-06-15 | Viper POD | GBL0007741.2.22 | Cloud Architect | Reporting | PBI-1046 | Cloud cost optimisation - slashing costs ruthlessly | 3 | 210 | per hour | 630
Deloitte UK | Gen. Melchett | 2026-06-16 | Viper POD | GBL0007741.2.22 | Cloud Architect | Notifications | PBI-1021 | Security posture review - ZERO tolerance for weakness | 3 | 210 | per hour | 630
Deloitte UK | Gen. Melchett | 2026-06-17 | Viper POD | GBL0007741.2.22 | Cloud Architect | User Management | PBI-1019 | Executive briefing - delivered with great authority | 3 | 210 | per hour | 630
Deloitte UK | Gen. Melchett | 2026-06-18 | Viper POD | GBL0007741.2.22 | Cloud Architect |  |  | AWS Well-Architected review - passed with flying colours | 4 | 210 | per hour | 840
Deloitte UK | Gen. Melchett | 2026-06-19 | Viper POD | GBL0007741.2.22 | Cloud Architect | Infrastructure | PBI-1033 | Security posture review - ZERO tolerance for weakness | 4 | 210 | per hour | 840
Deloitte UK | Gen. Melchett | 2026-06-22 | Viper POD | GBL0007741.2.22 | Cloud Architect | Reporting | PBI-1016 | Security posture review - ZERO tolerance for weakness | 4 | 210 | per hour | 840
Deloitte UK | Gen. Melchett | 2026-06-23 | Viper POD | GBL0007741.2.22 | Cloud Architect | User Management | PBI-1037 | Architecture decision record - brilliant insight | 3 | 210 | per hour | 630
Deloitte UK | Gen. Melchett | 2026-06-24 | Viper POD | GBL0007741.2.22 | Cloud Architect | Dashboard | PBI-1005 | Executive briefing - delivered with great authority | 4 | 210 | per hour | 840
Deloitte UK | Gen. Melchett | 2026-06-25 | Viper POD | GBL0007741.2.22 | Cloud Architect | Security |  | Executive briefing - delivered with great authority | 6 | 210 | per hour | 1260
Deloitte UK | Gen. Melchett | 2026-06-26 | Viper POD | GBL0007741.2.22 | Cloud Architect | Infrastructure | PBI-1042 | Technical strategy - bold and daring approach | 3 | 210 | per hour | 630
Deloitte UK | Gen. Melchett | 2026-06-30 | Viper POD | GBL0007741.2.22 | Cloud Architect | User Management | PBI-1041 | Technical strategy - bold and daring approach | 5 | 210 | per hour | 1050
Deloitte UK | Capt. Kevin Darling | 2026-06-01 | Viper POD | GBL0007741.2.22 | QA Test Lead | Security | PBI-1033 | Cloud infrastructure design - AWS | 6 | 120 | per hour | 720
Deloitte UK | Capt. Kevin Darling | 2026-06-02 | Viper POD | GBL0007741.2.22 | QA Test Lead | User Management | PBI-1010 | Figma wireframes review and iteration | 5 | 120 | per hour | 600
Deloitte UK | Capt. Kevin Darling | 2026-06-03 | Viper POD | GBL0007741.2.22 | QA Test Lead | Reporting | PBI-1021 | Cloud infrastructure design - AWS | 7 | 120 | per hour | 840
Deloitte UK | Capt. Kevin Darling | 2026-06-04 | Viper POD | GBL0007741.2.22 | QA Test Lead | User Management | PBI-1019 | UAT test case preparation | 6 | 120 | per hour | 720
Deloitte UK | Capt. Kevin Darling | 2026-06-05 | Viper POD | GBL0007741.2.22 | QA Test Lead | API Integration | PBI-1041 | Security review and penetration testing prep | 5 | 120 | per hour | 600
Deloitte UK | Capt. Kevin Darling | 2026-06-08 | Viper POD | GBL0007741.2.22 | QA Test Lead | Notifications | PBI-1020 | Cloud infrastructure design - AWS | 7 | 120 | per hour | 840
Deloitte UK | Capt. Kevin Darling | 2026-06-09 | Viper POD | GBL0007741.2.22 | QA Test Lead | Notifications | PBI-1011 | A/B testing framework setup | 5 | 120 | per hour | 600
Deloitte UK | Capt. Kevin Darling | 2026-06-10 | Viper POD | GBL0007741.2.22 | QA Test Lead | Notifications | PBI-1040 | Cloud infrastructure design - AWS | 6 | 120 | per hour | 720
Deloitte UK | Capt. Kevin Darling | 2026-06-11 | Viper POD | GBL0007741.2.22 | QA Test Lead | Authentication | PBI-1002 | Accessibility audit - WCAG 2.1 compliance | 7 | 120 | per hour | 840
Deloitte UK | Capt. Kevin Darling | 2026-06-12 | Viper POD | GBL0007741.2.22 | QA Test Lead | Notifications |  | UI component library development | 5 | 120 | per hour | 600
Deloitte UK | Capt. Kevin Darling | 2026-06-15 | Viper POD | GBL0007741.2.22 | QA Test Lead | API Integration |  | Design system documentation | 7 | 120 | per hour | 840
Deloitte UK | Capt. Kevin Darling | 2026-06-16 | Viper POD | GBL0007741.2.22 | QA Test Lead | Notifications | PBI-1002 | Accessibility audit - WCAG 2.1 compliance | 8 | 120 | per hour | 960
Deloitte UK | Capt. Kevin Darling | 2026-06-17 | Viper POD | GBL0007741.2.22 | QA Test Lead | User Management | PBI-1019 | Design system documentation | 8 | 120 | per hour | 960
Deloitte UK | Capt. Kevin Darling | 2026-06-18 | Viper POD | GBL0007741.2.22 | QA Test Lead | API Integration | PBI-1044 | UX research synthesis | 7 | 120 | per hour | 840
Deloitte UK | Capt. Kevin Darling | 2026-06-19 | Viper POD | GBL0007741.2.22 | QA Test Lead | Performance | PBI-1005 | Security review and penetration testing prep | 8 | 120 | per hour | 960
Deloitte UK | Capt. Kevin Darling | 2026-06-22 | Viper POD | GBL0007741.2.22 | QA Test Lead | Performance | PBI-1027 | Cloud infrastructure design - AWS | 5 | 120 | per hour | 600
Deloitte UK | Capt. Kevin Darling | 2026-06-23 | Viper POD | GBL0007741.2.22 | QA Test Lead | API Integration | PBI-1022 | UX research synthesis | 8 | 120 | per hour | 960
Deloitte UK | Capt. Kevin Darling | 2026-06-24 | Viper POD | GBL0007741.2.22 | QA Test Lead |  |  | UAT test case preparation | 6 | 120 | per hour | 720
Deloitte UK | Capt. Kevin Darling | 2026-06-25 | Viper POD | GBL0007741.2.22 | QA Test Lead | Infrastructure | PBI-1026 | Performance testing and optimisation | 7 | 120 | per hour | 840
Deloitte UK | Capt. Kevin Darling | 2026-06-26 | Viper POD | GBL0007741.2.22 | QA Test Lead | User Management | PBI-1036 | UAT test case preparation | 6 | 120 | per hour | 720
Deloitte UK | Capt. Kevin Darling | 2026-06-29 | Viper POD | GBL0007741.2.22 | QA Test Lead | API Integration | PBI-1030 | UAT test case preparation | 5 | 120 | per hour | 600
Deloitte UK | Capt. Kevin Darling | 2026-06-30 | Viper POD | GBL0007741.2.22 | QA Test Lead | Performance | PBI-1016 | Security review and penetration testing prep | 5 | 120 | per hour | 600
Deloitte UK | Bobbie Parkhurst | 2026-06-01 | Python POD | GBL0007741.2.33 | Full Stack Developer | Authentication | PBI-1019 | Data pipeline implementation | 7 | 125 | per hour | 875
Deloitte UK | Bobbie Parkhurst | 2026-06-02 | Python POD | GBL0007741.2.33 | Full Stack Developer | Security | PBI-1016 | Technical debt remediation | 9 | 125 | per hour | 1125
Deloitte UK | Bobbie Parkhurst | 2026-06-03 | Python POD | GBL0007741.2.33 | Full Stack Developer | Analytics | PBI-1047 | Kubernetes cluster configuration | 7 | 125 | per hour | 875
Deloitte UK | Bobbie Parkhurst | 2026-06-04 | Python POD | GBL0007741.2.33 | Full Stack Developer | Reporting | PBI-1032 | Microservices refactoring | 8 | 125 | per hour | 1000
Deloitte UK | Bobbie Parkhurst | 2026-06-05 | Python POD | GBL0007741.2.33 | Full Stack Developer | Data Migration | PBI-1032 | ETL pipeline debugging and tuning | 9 | 125 | per hour | 1125
Deloitte UK | Bobbie Parkhurst | 2026-06-08 | Python POD | GBL0007741.2.33 | Full Stack Developer | Security | PBI-1033 | Data pipeline implementation | 6 | 125 | per hour | 750
Deloitte UK | Bobbie Parkhurst | 2026-06-09 | Python POD | GBL0007741.2.33 | Full Stack Developer | API Integration | PBI-1038 | Microservices refactoring | 9 | 125 | per hour | 1125
Deloitte UK | Bobbie Parkhurst | 2026-06-10 | Python POD | GBL0007741.2.33 | Full Stack Developer | Authentication | PBI-1019 | API development - REST endpoints | 8 | 125 | per hour | 1000
Deloitte UK | Bobbie Parkhurst | 2026-06-11 | Python POD | GBL0007741.2.33 | Full Stack Developer | Notifications | PBI-1044 | Technical debt remediation | 9 | 125 | per hour | 1125
Deloitte UK | Bobbie Parkhurst | 2026-06-12 | Python POD | GBL0007741.2.33 | Full Stack Developer | User Management | PBI-1001 | Infrastructure as code - Terraform | 9 | 125 | per hour | 1125
Deloitte UK | Bobbie Parkhurst | 2026-06-15 | Python POD | GBL0007741.2.33 | Full Stack Developer | Reporting | PBI-1017 | Data quality framework implementation | 6 | 125 | per hour | 750
Deloitte UK | Bobbie Parkhurst | 2026-06-16 | Python POD | GBL0007741.2.33 | Full Stack Developer | Infrastructure | PBI-1003 | Data quality framework implementation | 8 | 125 | per hour | 1000
Deloitte UK | Bobbie Parkhurst | 2026-06-17 | Python POD | GBL0007741.2.33 | Full Stack Developer | Analytics | PBI-1036 | API development - REST endpoints | 9 | 125 | per hour | 1125
Deloitte UK | Bobbie Parkhurst | 2026-06-18 | Python POD | GBL0007741.2.33 | Full Stack Developer | User Management | PBI-1019 | Kubernetes cluster configuration | 7 | 125 | per hour | 875
Deloitte UK | Bobbie Parkhurst | 2026-06-19 | Python POD | GBL0007741.2.33 | Full Stack Developer | User Management | PBI-1029 | Data quality framework implementation | 6 | 125 | per hour | 750
Deloitte UK | Bobbie Parkhurst | 2026-06-22 | Python POD | GBL0007741.2.33 | Full Stack Developer | Notifications | PBI-1040 | Technical debt remediation | 8 | 125 | per hour | 1000
Deloitte UK | Bobbie Parkhurst | 2026-06-23 | Python POD | GBL0007741.2.33 | Full Stack Developer | Dashboard | PBI-1026 | Database schema optimisation | 6 | 125 | per hour | 750
Deloitte UK | Bobbie Parkhurst | 2026-06-24 | Python POD | GBL0007741.2.33 | Full Stack Developer | User Management | PBI-1024 | Kubernetes cluster configuration | 8 | 125 | per hour | 1000
Deloitte UK | Bobbie Parkhurst | 2026-06-25 | Python POD | GBL0007741.2.33 | Full Stack Developer | Analytics | PBI-1033 | Microservices refactoring | 7 | 125 | per hour | 875
Deloitte UK | Bobbie Parkhurst | 2026-06-26 | Python POD | GBL0007741.2.33 | Full Stack Developer | Authentication | PBI-1003 | Code review and PR management | 9 | 125 | per hour | 1125
Deloitte UK | Bobbie Parkhurst | 2026-06-29 | Python POD | GBL0007741.2.33 | Full Stack Developer |  |  | Database schema optimisation | 6 | 125 | per hour | 750
Deloitte UK | Bobbie Parkhurst | 2026-06-30 | Python POD | GBL0007741.2.33 | Full Stack Developer | User Management | PBI-1030 | ETL pipeline debugging and tuning | 8 | 125 | per hour | 1000
Deloitte UK | Doris Miggins | 2026-06-01 | Python POD | GBL0007741.2.33 | Data Engineer | User Management | PBI-1009 | Technical debt remediation | 7 | 135 | per hour | 945
Deloitte UK | Doris Miggins | 2026-06-02 | Python POD | GBL0007741.2.33 | Data Engineer | Infrastructure | PBI-1011 | Technical debt remediation | 8 | 135 | per hour | 1080
Deloitte UK | Doris Miggins | 2026-06-03 | Python POD | GBL0007741.2.33 | Data Engineer |  |  | Technical debt remediation | 9 | 135 | per hour | 1215
Deloitte UK | Doris Miggins | 2026-06-04 | Python POD | GBL0007741.2.33 | Data Engineer | Infrastructure | PBI-1033 | Technical debt remediation | 8 | 135 | per hour | 1080
Deloitte UK | Doris Miggins | 2026-06-05 | Python POD | GBL0007741.2.33 | Data Engineer | Analytics | PBI-1020 | Documentation - Confluence update | 9 | 135 | per hour | 1215
Deloitte UK | Doris Miggins | 2026-06-08 | Python POD | GBL0007741.2.33 | Data Engineer | Infrastructure | PBI-1022 | API development - REST endpoints | 9 | 135 | per hour | 1215
Deloitte UK | Doris Miggins | 2026-06-09 | Python POD | GBL0007741.2.33 | Data Engineer | Analytics | PBI-1020 | Data quality framework implementation | 6 | 135 | per hour | 810
Deloitte UK | Doris Miggins | 2026-06-10 | Python POD | GBL0007741.2.33 | Data Engineer | Performance | PBI-1017 | Technical debt remediation | 6 | 135 | per hour | 810
Deloitte UK | Doris Miggins | 2026-06-11 | Python POD | GBL0007741.2.33 | Data Engineer | Authentication | PBI-1038 | Documentation - Confluence update | 7 | 135 | per hour | 945
Deloitte UK | Doris Miggins | 2026-06-12 | Python POD | GBL0007741.2.33 | Data Engineer | User Management | PBI-1041 | Database schema optimisation | 9 | 135 | per hour | 1215
Deloitte UK | Doris Miggins | 2026-06-15 | Python POD | GBL0007741.2.33 | Data Engineer | Notifications | PBI-1016 | Database schema optimisation | 9 | 135 | per hour | 1215
Deloitte UK | Doris Miggins | 2026-06-16 | Python POD | GBL0007741.2.33 | Data Engineer |  |  | Technical debt remediation | 6 | 135 | per hour | 810
Deloitte UK | Doris Miggins | 2026-06-17 | Python POD | GBL0007741.2.33 | Data Engineer | Authentication | PBI-1029 | Microservices refactoring | 6 | 135 | per hour | 810
Deloitte UK | Doris Miggins | 2026-06-18 | Python POD | GBL0007741.2.33 | Data Engineer | Reporting | PBI-1027 | Data quality framework implementation | 8 | 135 | per hour | 1080
Deloitte UK | Doris Miggins | 2026-06-19 | Python POD | GBL0007741.2.33 | Data Engineer | User Management |  | Data quality framework implementation | 7 | 135 | per hour | 945
Deloitte UK | Doris Miggins | 2026-06-22 | Python POD | GBL0007741.2.33 | Data Engineer |  |  | Documentation - Confluence update | 9 | 135 | per hour | 1215
Deloitte UK | Doris Miggins | 2026-06-23 | Python POD | GBL0007741.2.33 | Data Engineer | Reporting | PBI-1034 | Documentation - Confluence update | 6 | 135 | per hour | 810
Deloitte UK | Doris Miggins | 2026-06-24 | Python POD | GBL0007741.2.33 | Data Engineer | Infrastructure | PBI-1043 | Code review and PR management | 7 | 135 | per hour | 945
Deloitte UK | Doris Miggins | 2026-06-25 | Python POD | GBL0007741.2.33 | Data Engineer | Security | PBI-1021 | Code review and PR management | 9 | 135 | per hour | 1215
Deloitte UK | Doris Miggins | 2026-06-26 | Python POD | GBL0007741.2.33 | Data Engineer | User Management | PBI-1022 | ETL pipeline debugging and tuning | 7 | 135 | per hour | 945
Deloitte UK | Doris Miggins | 2026-06-29 | Python POD | GBL0007741.2.33 | Data Engineer |  |  | Monitoring and alerting setup - Datadog | 8 | 135 | per hour | 1080
Deloitte UK | Doris Miggins | 2026-06-30 | Python POD | GBL0007741.2.33 | Data Engineer | Performance | PBI-1013 | Technical debt remediation | 8 | 135 | per hour | 1080
Deloitte UK | Lord Percy Percy | 2026-06-01 | Python POD | GBL0007741.2.33 | DevOps Engineer | User Management | PBI-1020 | Infrastructure as code - Terraform | 6 | 145 | per hour | 870
Deloitte UK | Lord Percy Percy | 2026-06-02 | Python POD | GBL0007741.2.33 | DevOps Engineer | Data Migration | PBI-1046 | Infrastructure as code - Terraform | 6 | 145 | per hour | 870
Deloitte UK | Lord Percy Percy | 2026-06-03 | Python POD | GBL0007741.2.33 | DevOps Engineer |  |  | Documentation - Confluence update | 6 | 145 | per hour | 870
Deloitte UK | Lord Percy Percy | 2026-06-04 | Python POD | GBL0007741.2.33 | DevOps Engineer | Performance | PBI-1023 | Kubernetes cluster configuration | 8 | 145 | per hour | 1160
Deloitte UK | Lord Percy Percy | 2026-06-05 | Python POD | GBL0007741.2.33 | DevOps Engineer | Dashboard | PBI-1037 | Infrastructure as code - Terraform | 7 | 145 | per hour | 1015
Deloitte UK | Lord Percy Percy | 2026-06-08 | Python POD | GBL0007741.2.33 | DevOps Engineer | Infrastructure |  | Data quality framework implementation | 8 | 145 | per hour | 1160
Deloitte UK | Lord Percy Percy | 2026-06-09 | Python POD | GBL0007741.2.33 | DevOps Engineer | Authentication | PBI-1019 | Infrastructure as code - Terraform | 6 | 145 | per hour | 870
Deloitte UK | Lord Percy Percy | 2026-06-10 | Python POD | GBL0007741.2.33 | DevOps Engineer | Performance | PBI-1042 | Kubernetes cluster configuration | 5 | 145 | per hour | 725
Deloitte UK | Lord Percy Percy | 2026-06-11 | Python POD | GBL0007741.2.33 | DevOps Engineer | Performance | PBI-1014 | Documentation - Confluence update | 7 | 145 | per hour | 1015
Deloitte UK | Lord Percy Percy | 2026-06-12 | Python POD | GBL0007741.2.33 | DevOps Engineer | Data Migration | PBI-1036 | Code review and PR management | 6 | 145 | per hour | 870
Deloitte UK | Lord Percy Percy | 2026-06-15 | Python POD | GBL0007741.2.33 | DevOps Engineer | Dashboard | PBI-1040 | Database schema optimisation | 7 | 145 | per hour | 1015
Deloitte UK | Lord Percy Percy | 2026-06-16 | Python POD | GBL0007741.2.33 | DevOps Engineer | Authentication | PBI-1043 | Microservices refactoring | 6 | 145 | per hour | 870
Deloitte UK | Lord Percy Percy | 2026-06-17 | Python POD | GBL0007741.2.33 | DevOps Engineer | API Integration | PBI-1004 | Monitoring and alerting setup - Datadog | 6 | 145 | per hour | 870
Deloitte UK | Lord Percy Percy | 2026-06-18 | Python POD | GBL0007741.2.33 | DevOps Engineer | Infrastructure | PBI-1046 | Data quality framework implementation | 5 | 145 | per hour | 725
Deloitte UK | Lord Percy Percy | 2026-06-19 | Python POD | GBL0007741.2.33 | DevOps Engineer | Notifications |  | Data pipeline implementation | 8 | 145 | per hour | 1160
Deloitte UK | Lord Percy Percy | 2026-06-22 | Python POD | GBL0007741.2.33 | DevOps Engineer | User Management | PBI-1011 | API development - REST endpoints | 6 | 145 | per hour | 870
Deloitte UK | Lord Percy Percy | 2026-06-23 | Python POD | GBL0007741.2.33 | DevOps Engineer | Performance | PBI-1031 | Monitoring and alerting setup - Datadog | 8 | 145 | per hour | 1160
Deloitte UK | Lord Percy Percy | 2026-06-24 | Python POD | GBL0007741.2.33 | DevOps Engineer | Infrastructure | PBI-1019 | Infrastructure as code - Terraform | 6 | 145 | per hour | 870
Deloitte UK | Lord Percy Percy | 2026-06-25 | Python POD | GBL0007741.2.33 | DevOps Engineer | Notifications | PBI-1037 | Data pipeline implementation | 5 | 145 | per hour | 725
Deloitte UK | Lord Percy Percy | 2026-06-26 | Python POD | GBL0007741.2.33 | DevOps Engineer |  |  | Code review and PR management | 6 | 145 | per hour | 870
Deloitte UK | Lord Percy Percy | 2026-06-29 | Python POD | GBL0007741.2.33 | DevOps Engineer | Security | PBI-1012 | Database schema optimisation | 5 | 145 | per hour | 725
Deloitte UK | Lord Percy Percy | 2026-06-30 | Python POD | GBL0007741.2.33 | DevOps Engineer | Performance | PBI-1012 | Data quality framework implementation | 5 | 145 | per hour | 725
Deloitte UK | Mrs. Miggins | 2026-06-01 | Cobra POD | GBL0007741.2.11 | Business Analyst | Authentication | PBI-1020 | Requirements gathering - stakeholder interviews | 6 | 115 | per hour | 690
Deloitte UK | Mrs. Miggins | 2026-06-02 | Cobra POD | GBL0007741.2.11 | Business Analyst | Data Migration | PBI-1030 | Risk register update and mitigation planning | 4 | 115 | per hour | 460
Deloitte UK | Mrs. Miggins | 2026-06-03 | Cobra POD | GBL0007741.2.11 | Business Analyst | User Management | PBI-1030 | User story refinement with client team | 7 | 115 | per hour | 805
Deloitte UK | Mrs. Miggins | 2026-06-04 | Cobra POD | GBL0007741.2.11 | Business Analyst | Dashboard | PBI-1022 | Cunning plan implementation - phase 2 | 6 | 115 | per hour | 690
Deloitte UK | Mrs. Miggins | 2026-06-05 | Cobra POD | GBL0007741.2.11 | Business Analyst | Performance | PBI-1042 | Project governance documentation | 5 | 115 | per hour | 575
Deloitte UK | Mrs. Miggins | 2026-06-08 | Cobra POD | GBL0007741.2.11 | Business Analyst | Reporting | PBI-1001 | Project governance documentation | 6 | 115 | per hour | 690
Deloitte UK | Mrs. Miggins | 2026-06-09 | Cobra POD | GBL0007741.2.11 | Business Analyst | Analytics | PBI-1044 | Stakeholder presentation preparation | 6 | 115 | per hour | 690
Deloitte UK | Mrs. Miggins | 2026-06-10 | Cobra POD | GBL0007741.2.11 | Business Analyst | Analytics | PBI-1041 | User story refinement with client team | 5 | 115 | per hour | 575
Deloitte UK | Mrs. Miggins | 2026-06-11 | Cobra POD | GBL0007741.2.11 | Business Analyst | User Management | PBI-1021 | Client status report and dashboard update | 7 | 115 | per hour | 805
Deloitte UK | Mrs. Miggins | 2026-06-12 | Cobra POD | GBL0007741.2.11 | Business Analyst | Notifications | PBI-1007 | Client status report and dashboard update | 4 | 115 | per hour | 460
Deloitte UK | Mrs. Miggins | 2026-06-15 | Cobra POD | GBL0007741.2.11 | Business Analyst | Performance | PBI-1021 | User story refinement with client team | 5 | 115 | per hour | 575
Deloitte UK | Mrs. Miggins | 2026-06-16 | Cobra POD | GBL0007741.2.11 | Business Analyst | Data Migration | PBI-1025 | Requirements gathering - stakeholder interviews | 5 | 115 | per hour | 575
Deloitte UK | Mrs. Miggins | 2026-06-17 | Cobra POD | GBL0007741.2.11 | Business Analyst | Data Migration | PBI-1022 | Architecture review board preparation | 5 | 115 | per hour | 575
Deloitte UK | Mrs. Miggins | 2026-06-18 | Cobra POD | GBL0007741.2.11 | Business Analyst |  |  | Change request assessment and documentation | 6 | 115 | per hour | 690
Deloitte UK | Mrs. Miggins | 2026-06-19 | Cobra POD | GBL0007741.2.11 | Business Analyst | Notifications | PBI-1024 | Stakeholder presentation preparation | 4 | 115 | per hour | 460
Deloitte UK | Mrs. Miggins | 2026-06-22 | Cobra POD | GBL0007741.2.11 | Business Analyst | Notifications | PBI-1008 | Requirements gathering - stakeholder interviews | 5 | 115 | per hour | 575
Deloitte UK | Mrs. Miggins | 2026-06-23 | Cobra POD | GBL0007741.2.11 | Business Analyst | Reporting | PBI-1026 | Stakeholder presentation preparation | 7 | 115 | per hour | 805
Deloitte UK | Mrs. Miggins | 2026-06-24 | Cobra POD | GBL0007741.2.11 | Business Analyst | Dashboard | PBI-1041 | Project governance documentation | 6 | 115 | per hour | 690
Deloitte UK | Mrs. Miggins | 2026-06-25 | Cobra POD | GBL0007741.2.11 | Business Analyst | Analytics | PBI-1015 | Risk register update and mitigation planning | 6 | 115 | per hour | 690
Deloitte UK | Mrs. Miggins | 2026-06-26 | Cobra POD | GBL0007741.2.11 | Business Analyst | Performance | PBI-1010 | User story refinement with client team | 5 | 115 | per hour | 575
Deloitte UK | Mrs. Miggins | 2026-06-29 | Cobra POD | GBL0007741.2.11 | Business Analyst | Analytics | PBI-1024 | Project governance documentation | 7 | 115 | per hour | 805
Deloitte UK | Mrs. Miggins | 2026-06-30 | Cobra POD | GBL0007741.2.11 | Business Analyst | User Management | PBI-1031 | Project governance documentation | 7 | 115 | per hour | 805
Formulas:
Week num = ISOWEEKNUM([Date])